## Slide 1: Executive Summary
The ERP System Update project is a strategic initiative designed to modernize and integrate back-office functions including finance, human resources (HR), procurement, and operations. This project aims to enhance overall efficiency, data accuracy, and scalability, aligning with the organization’s commitment to innovation and operational excellence. By leveraging advanced technology and streamlined processes, the ERP System Update will significantly improve the company’s internal operations and support its long-term growth objectives.
Current Phases:
Planning: Completed
Designing: Completed
Integration: 67% In Progress
Testing: On Hold
Projected Launch Date: 81 Days (Friday, September 19)
Root Causes:
Inadequate initial scope definition and risk assessment.
Vendor underperformance and delays.
Insufficient resource allocation.

## Slide 2: ERP Status Report
Scope of Work |  | 
Employee(DEPT) | Task | Workload
Kate(Finance) | Budget Tracking and Reallocation | 55%
Georg & Richard(IT) | System Architecture and Data Migration and Integration Testing | 46%
Nancy(HR) | Data Management and Payroll System Update | 40%
Paula(PRO) | Vendor Management & Contract Renegotiation | 40%
Overdue Tasks |  | 
Overdue | Task | Deadline
6 Weeks | Integration of Remaining Modules | 2024-05-24
3 Weeks | Conduct thorough UAT | 2024-06-15
1 Week | Deploy the System to Production | 2024-06-26
Chart: 
Total budget | 1000000
Revised budget | 1200000
Budget used | 800000
Total Budget
$1,000,000
Current Status
20% Over Target
Project Budget
Chart: 
| Georg | Nancy | Richard | Kate | Paula
Column1 | 0.67 | 0.55 | 0 | 0.7 | 0.4
Workload
Expense ($)
Workload (%)
Employees
81 Days
Friday, September 19
Projected Launch Date
Testing
On Hold
Planning
Completed
Designing
Completed
Integration
In Progress
Chart: 
| In progress
Development | 0.67 | 0.33
67%

## Slide 3: Action Plan
-Vendor Engagement: Ongoing; expected resolution by July 8, 2024. -Resource Reallocation: In progress; expected stabilization by July 31, 2024. -Budget Review and Reallocation: Underway; completion by July 10, 2024. -Stakeholder Communication: Enhanced; ongoing with full alignment by July 15, 2024.
- Implement enhanced risk management and contingency planning. - Establish stronger governance frameworks for vendor management.
CIO’s Assistance Needed: 1. Approval for Additional Budget: Immediate approval of the revised budget. 2. Support in Vendor Negotiations: Expedite vendor performance. 3. Reallocate existing skilled personnel and hire additional contractors.